## Detailed Task Allocation
Name | Role | Working Domain | Phase 1 (Detailed Task) | Phase 2 (Detailed Task) | Phase 3 (Detailed Task) | Phase 4 (Detailed Task) | Phase 5
Ishan Pankaj Jadhav | Team Lead / AI Dev | Architecture + AI Integration | Design complete system architecture and define APIs for all modules | Supervise integration of CV models and ensure pipeline compatibility | Lead integration of all modules and implement decision engine logic | Handle deployment setup using Docker and optimize system flow | Implement model versioning and design system scalability for multiple users
Kodati Ramya Sree | Intern | Data + Analytics | Design and implement database schema for storing interview data | Store and analyze alert logs for suspicious activity tracking | Support data fusion by combining multiple model outputs | Build analytics dashboards using Power BI or similar tools | Develop PDF report generation and advanced analytics insights
Shambhavi M K | Intern | Backend Development | Develop backend APIs for session handling and response submission | Implement WebSocket communication for real-time video streaming | Integrate backend APIs with AI modules and frontend | Perform testing, debugging, and ensure API reliability | Implement authentication system and role-based access control
Messiah Prince N | Intern | AI/NLP | Integrate basic NLP model for question-answer interaction | Assist in emotion detection model integration | Develop scoring logic for evaluating candidate responses | Tune models for better accuracy and performance | Integrate speech-to-text system for audio processing
Ganga Siva Prasad | Intern | Data Structures + CV | Implement data structures for storing responses efficiently | Assist in face detection model implementation | Develop behavior tracking logic for suspicious activity | Optimize algorithms for faster processing | Implement eye tracking and gaze detection system
Aditya Gour | Intern | API + Automation | Integrate frontend with backend APIs | Develop alert APIs for triggering notifications | Connect all modules using API communication | Automate workflows using tools like n8n | Implement session recovery and workflow automation
Akshat Rana | AI/ML Dev | Full Stack + CV | Develop frontend UI and assist backend setup | Implement object detection using YOLO model | Handle full system integration across modules | Optimize performance and reduce latency | Implement multi-user handling and performance tuning
Aditi Yadav | AI/ML Intern | Full Stack + DevOps | Develop candidate-side frontend UI | Assist in integrating computer vision models | Develop admin panel backend functionalities | Support DevOps tasks and environment setup | Handle cloud deployment and CI/CD pipeline setup
Yash Wankhede | AI Dev | Data + Visualization | Perform data preprocessing for system inputs | Analyze alert data and generate insights | Develop visualization for scoring system | Build dashboards for analytics display | Implement bias analysis and advanced data insights
Ishan Dudhat | AI Intern | CV + Streaming | Implement camera integration for video capture | Develop image processing pipeline | Integrate real-time video streaming system | Optimize system for smooth streaming | Implement offline handling and data buffering
Adityaraj Vikramsingh Jadhav | AI Intern | AI Support | Assist in NLP flow and response handling | Support object detection model tasks | Assist in integration of all modules | Perform testing and debugging | Develop smart alert prioritization system
Kaveri Ravi Desai | AI/ML Intern | AI + Evaluation | Assist NLP model and database integration | Support emotion detection model tasks | Develop evaluation metrics for scoring | Generate detailed candidate reports | Implement voice analysis for stress detection
Radhika Gupta | AI/ML Intern | Data + Documentation | Handle data processing and Excel tracking | Track alert data and maintain logs | Assist in report generation | Prepare system documentation | Develop user guides and final documentation